## POA&M FY2026
Weakness ID | System Name | Weakness Name | Weakness Description | CVE | CVSS Score | Risk Rating | Remediation Tier | SLA (Days) | Affected Host(s) | Port / Protocol | NIST 800-53 Control(s) | Point of Contact | Organization | Date Identified | Scheduled Completion Date | Milestone | Status | Days Open | Overdue | Delay Reason | KEV Match | Exploit Available | Asset Tier | Risk Priority Score | Recommended Solution | References
FY2026-C-0001 | DOT-OCIO-PROD | MS17-010 EternalBlue SMB RCE | Remote code execution vulnerability in SMBv1 | CVE-2024-1234 | 9.8 | High | P2 | 30 | 10.0.0.15 | 445 / tcp | SI-2, CM-7, SC-7 | System Owner | Department of Transportation | 2026-05-19 | 2026-06-03 | 1. Validate and triage findings — Day 5 2. Assign to system owner — Day 7 3. Schedule patch in change management — Day 14 4. Apply patch — Day 25 5. Re-scan and close — 2026-06-03 | Open | 0 | NO |  | NO | YES | unknown | 64.3 | Apply Microsoft patch MS17-010 immediately. Disable SMBv1 if not required. | https://docs.microsoft.com/en-us/security-updates/securitybulletins/2017/ms17-010
FY2026-C-0002 | DOT-OCIO-PROD | Apache Tomcat AJP File Inclusion (Ghostcat) | AJP connector exposes internal files | CVE-2024-8901 | 9.1 | High | P2 | 30 | 10.0.0.88 | 8080 / tcp | SI-2, CM-7 | System Owner | Department of Transportation | 2026-05-19 | 2026-06-03 | 1. Validate and triage findings — Day 5 2. Assign to system owner — Day 7 3. Schedule patch in change management — Day 14 4. Apply patch — Day 25 5. Re-scan and close — 2026-06-03 | Open | 0 | NO |  | NO | YES | unknown | 61.8 | Upgrade to Tomcat 9.0.31, 8.5.51, or 7.0.100. Disable AJP connector if not needed. | https://tomcat.apache.org/security-9.html
FY2026-H-0003 | DOT-OCIO-PROD | RDP BlueKeep Vulnerability | Remote Desktop Services RCE | CVE-2024-5678 | 8.8 | Moderate | P3 | 90 | 10.0.0.22 | 3389 / tcp | AC-17, SI-2, CM-7 | System Owner | Department of Transportation | 2026-05-19 | 2026-06-18 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-06-18 | Open | 0 | NO |  | NO | NO | unknown | 45.8 | Apply Windows security update KB4499175. | https://portal.msrc.microsoft.com/en-US/security-guidance/advisory/CVE-2019-0708
FY2026-H-0004 | DOT-OCIO-PROD | Windows Print Spooler RCE (PrintNightmare) | Print spooler service allows privilege escalation | CVE-2024-4455 | 8.1 | Moderate | P3 | 90 | 10.0.0.22 | 445 / tcp | SI-2, CM-7, AC-6 | System Owner | Department of Transportation | 2026-05-19 | 2026-06-18 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-06-18 | Open | 0 | NO |  | NO | NO | unknown | 43.3 | Apply KB5005010. Disable Print Spooler on systems that do not require it. | https://msrc.microsoft.com/update-guide/vulnerability/CVE-2021-34527
FY2026-H-0005 | DOT-OCIO-PROD | Apache Log4j RCE (Log4Shell) | JNDI injection vulnerability in Apache Log4j | CVE-2024-9101 | 7.5 | Moderate | P3 | 90 | 10.0.0.33 | 443 / tcp | SI-2, SI-10 | System Owner | Department of Transportation | 2026-05-19 | 2026-06-18 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-06-18 | Open | 0 | NO |  | NO | NO | unknown | 41.2 | Upgrade to Log4j 2.17.1 or later. Apply vendor patches. | https://logging.apache.org/log4j/2.x/security.html
FY2026-H-0006 | DOT-OCIO-PROD | MySQL Unpatched Version | MySQL server running outdated version with known vulnerabilities | CVE-2024-2233 | 7.2 | Moderate | P3 | 90 | 10.0.0.15 | 3306 / tcp | SI-2, SI-2(2) | System Owner | Department of Transportation | 2026-05-19 | 2026-06-18 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-06-18 | Open | 0 | NO |  | NO | NO | unknown | 40.2 | Upgrade MySQL to the latest stable release. | https://dev.mysql.com/doc/relnotes/mysql/8.0/en/
FY2026-M-0007 | DOT-OCIO-PROD | SSL/TLS Weak Cipher Suites | Server supports weak cryptographic algorithms | CVE-2024-5566 | 6.8 | Moderate | P3 | 90 | 10.0.0.33 | 443 / tcp | SC-8, SC-28, SI-2 | System Owner | Department of Transportation | 2026-05-19 | 2026-08-17 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-08-17 | Open | 0 | NO |  | NO | NO | unknown | 38.8 | Reconfigure the SSL/TLS service to disable weak cipher suites. Enforce TLS 1.2 or higher. | https://tools.ietf.org/html/rfc7525
FY2026-M-0008 | DOT-OCIO-PROD | Apache HTTP Server mod_status Information Disclosure | Sensitive information exposed via server-status page | CVE-2024-1122 | 6.5 | Moderate | P3 | 90 | 10.0.0.44 | 80 / tcp | SI-2, CM-7 | System Owner | Department of Transportation | 2026-05-19 | 2026-08-17 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-08-17 | Open | 0 | NO |  | NO | NO | unknown | 37.8 | Restrict access to /server-status to trusted hosts only. Disable mod_status if not required. | https://httpd.apache.org/docs/current/mod/mod_status.html
FY2026-M-0009 | DOT-OCIO-PROD | OpenSSH Username Enumeration | SSH user enumeration via timing attack | CVE-2024-3344 | 5.3 | Moderate | P3 | 90 | 10.0.0.55 | 22 / tcp | IA-5, AC-7 | System Owner | Department of Transportation | 2026-05-19 | 2026-08-17 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-08-17 | Open | 0 | NO |  | NO | NO | unknown | 33.5 | Upgrade OpenSSH to 7.8 or later. | https://www.openssh.com/txt/release-7.8
FY2026-M-0010 | DOT-OCIO-PROD | TLS/SSL Certificate Expired | SSL certificate has expired | CVE-2024-6677 | 4.3 | Moderate | P3 | 90 | 10.0.0.66 | 443 / tcp | SC-8, SC-28, SI-2 | System Owner | Department of Transportation | 2026-05-19 | 2026-08-17 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-08-17 | Open | 0 | NO |  | NO | NO | unknown | 30 | Renew the SSL certificate immediately. | https://tools.ietf.org/html/rfc5280
FY2026-L-0011 | DOT-OCIO-PROD | SNMP Default Community String | SNMP service using default community strings | CVE-2024-7890 | 3.7 | Moderate | P3 | 90 | 10.0.0.77 | 161 / tcp | CM-7, IA-3 | System Owner | Department of Transportation | 2026-05-19 | 2026-11-15 | 1. Validate findings — Week 1 2. Assign to system owner — Week 2 3. Remediation scheduled — Week 6 4. Patch applied — Week 10 5. Close POA&M — 2026-11-15 | Open | 0 | NO |  | NO | NO | unknown | 27.9 | Disable SNMP or change community strings to complex values. Use SNMPv3 with authentication. | https://tools.ietf.org/html/rfc3414
FY2026-L-0012 | DOT-OCIO-PROD | Telnet Service Detected | Unencrypted remote access protocol detected | N/A | 2.1 | Low | P4 | 180 | 10.0.0.99 | 23 / tcp | CM-7, SC-8, AC-17 | System Owner | Department of Transportation | 2026-05-19 | 2026-11-15 | 1. Document accepted risk or remediation path — Month 1 2. Schedule remediation — Month 3 3. Apply fix — Month 5 4. Close POA&M — 2026-11-15 | Open | 0 | NO |  | NO | NO | unknown | 22.4 | Disable Telnet. Use SSH for encrypted remote access. | https://tools.ietf.org/html/rfc854

## Metadata
Field | Value
System Name | DOT-OCIO-PROD
System Owner | System Owner
Organization | Department of Transportation
Fiscal Year | FY2026
Generated Date | 2026-05-19
Total Findings | 12
Framework | NIST SP 800-53 Rev 5 / FISMA